# Full-Stack Casino Development - 1 Month Execution Plan

Scope: Backend + Frontend (UI adaptable when final design arrives)

Goal: Deliver functional casino platform with dashboard, payment system, admin panel, and 10 lightweight games.

## Monthly Overview

Week 1: Core system (Authentication, Wallet, Payment, Basic Dashboard UI + APIs).

Week 2: Game Engine + 5 Games (Backend + Basic Frontend Integration).

Week 3: Remaining 5 Games + Provably Fair + UI Improvements.

Week 4: Security Hardening, Admin Enhancements, Testing, Deployment.

## Week 1: Account, Wallet, Payment, Dashboard Foundation

Day 1: Finalize architecture, database schema (users, ledger, deposits, withdrawals, bets, games). Setup project structure (backend + frontend).

Day 2: Implement authentication (register, login, JWT, roles). Create basic frontend auth pages (login/register placeholders).

Day 3: Build secure wallet core (atomic balance updates, ledger logging). Connect frontend dashboard layout structure.

Day 4: Implement deposit & withdrawal APIs (manual approval). Create frontend wallet pages (balance + transaction table).

Day 5: Build admin APIs (approve/reject withdrawals, view users). Create simple admin panel layout.

Day 6: Implement dashboard APIs (summary, statistics). Connect frontend dashboard with real API data.

Day 7: Add baseline security (validation, rate limit, logging). Test full user flow end-to-end.

## Week 2: Game Engine + 5 Games

Day 8: Build universal game engine (bet validation, RNG, payout calculation, ledger update).

Day 9: Implement Dice (backend logic + frontend basic UI).

Day 10: Implement Coin Flip (backend + frontend).

Day 11: Implement Limbo (backend + frontend).

Day 12: Implement Hi-Lo (backend + frontend).

Day 13: Implement Crash (backend + frontend basic version).

Day 14: Integration testing of all 5 games.

## Week 3: Remaining 5 Games + Provably Fair

Day 15: Implement Roulette (backend + frontend).

Day 16: Implement Keno (backend + frontend).

Day 17: Implement Wheel game.

Day 18: Implement Plinko (basic math version).

Day 19: Implement Slots (basic RNG version).

Day 20: Build provably fair system (server seed, client seed, hash reveal).

Day 21: UI refinement (replace placeholders with updated UI design if provided).

## Week 4: Hardening, Testing, Deployment

Day 22: Enhance logging, audit logs for admin actions.

Day 23: Add anti-abuse protections (bet frequency limit, max bet rules).

Day 24: Stress test wallet & betting logic (concurrent request simulation).

Day 25: Optimize queries and performance.

Day 26: Dockerize backend and frontend.

Day 27: Setup production server (Nginx, HTTPS, environment config).

Day 28: Final UI polish based on latest design update.

Day 29: Bug fixing and system stabilization.

Day 30: Documentation, deployment verification, handover preparation.